## Sheet1
Product Backlog & User Story
ID | Epic | As a … | I Want to … | So that … | Priority | Estimation
1c | Login/Registration | Customer | log into the application without entering personal information like bank account | I can save time and have a seamless experience | HIGH | 5
2c | View recommended places | Customer | view the most recommended places | I can easily find and book the best places destination | MEDIUM | 3
3c | Book hotel | Customer | make sure the hotel that I have booked was the correct hotel | I can choose the hotel I want | HIGH | 5
1d | User Experience | Developer | an attractive and user-friendly design | the customer can feel comfortable to use the app | MEDIUM | 3
4c | Hotel Information | Customer | information about the hotel's facilities | I can decide if the hotel meets my requirements | MEDIUM | 3
5c | View Profile | Customer | view my profile information (name, profile picture, phone number, address, gender, email) on the profile screen | I can easily access and verify my personal information | MEDIUM | 3
6c | Logout | Customer | have a logout button that navigates me to the login screen when pressed | I can securely log out of the application | LOW | 2
Sprint Planning
Sprint 1 |  | Sprint 2
Sprint Goals : |  | Sprint Goals :
1 | Customer can save time | 1 | Customers can choose the hotel they want
2 | Customer can easily see recommended places | 2 | Customers feel comfortable while using the application
|  | 3 | Customer can view the profile
Sprint Backlog : |  | Sprint Backlog :
ID | Backlog Items | ID | Backlog Items
1c | As a customer I want to enter the application without keep entering my personal information like bank account, etc | 3c | As a CUSTOMER I want to make sure the hotel that I have booked was the correct hotel and the payment method is based on my preferences
2c | As a customer I want to view the most recommended places to holiday | 5c | As a customer, I want to see my profile information (name, profile picture, phone number, address, gender, email) on the profile screen.
1d | As a DEVELOPER I want an attractive and user-friendly design so that the CUSTOMER can feel comfortable to use the app rather than use another similar app | 6c | have a logout button that navigates me to the login screen when pressed
Daily Scrum Meeting Report
No. | Nama Anggota | Task yang dikerjakan | Tanggal Pengerjaan | Kendala yang dihadapi | Waktu Perkiraan Selesai
1 | Irfan | Membuat design UI di Figma | 2024-04-09 | Kesulitan menentukan tata letak yang pas | 3 minggu
2 | Elroy | Membuat halaman registrasi dan login | 2024-04-09 | Susah menentukan validasi yang cocok | 1 minggu
3 | Louis | Membuat checkout | 2024-04-09 | kesulitan mengimplementasikan provider | 1 minggu
Sprint Review
Sprint 1 |  | Sprint 2
Completed Task | Incompleted Task | Completed Task | Incompleted Task | What's Next
Design UI for AuthScreen, Login, Register, Home and Detail page. Coding for AuthScreen, make a Product Overview page | Coding for Login, Register. Coding for Main Menu Page | Design UI for Profil | Design for Payment and checkout, Coding for Profil screen, Coding for Payment page. | Sprint 3 : Sprint Goal 1 : Customer can easily see the available facilities
Sprint Retrospective
Sprint 1
Analysis |  | Actions
What went well? | What could be improved? | What to stop doing? | What to Keep doing? | What to Start doing?
Fair Task Allocation | Start on time | Sudden change | Daily Scrum Meeting | Pair programming
Sprint 2
Analysis |  | Actions
What went well? | What could be improved? | What to stop doing? | What to Keep doing? | What to Start doing?
Open Communication | Time estimation accuracy | Unproductive meetings | Agile practices | Regular retrospectives