## Sheet1
Product Backlog & User Story
ID | Epic | As a … | I Want to … | So that … | Priority | Estimation
1c | Login/Registration | Customer | log into the application without entering personal information like bank account | I can save time and have a seamless experience | HIGH | 5
2c | View recommended places | Customer | view the most recommended places | I can easily find and book the best places destination | MEDIUM | 3
3c | Book hotel | Customer | make sure the hotel that I have booked was the correct hotel | I can choose the hotel I want | HIGH | 5
1d | User Experience | Developer | an attractive and user-friendly design | the customer can feel comfortable to use the app | MEDIUM | 3
4c | Hotel Information | Customer | information about the hotel's facilities | I can decide if the hotel meets my requirements | MEDIUM | 3
5c | View Profile | Customer | view my profile information (name, profile picture, phone number, address, gender, email) on the profile screen | I can easily access and verify my personal information | MEDIUM | 3
6c | Logout | Customer | have a logout button that navigates me to the login screen when pressed | I can securely log out of the application | LOW | 2
Sprint Planning
Sprint 1
Sprint Goals : |  | TAMBAHKAN SPRINT 2, SPRINT 3 DST
1 | Seller can view product
2 | ….
Sprint Backlog :
ID | Backlog Items
123 | As a seller I want to view product …
Daily Scrum Meeting Report | [5 empty] | TABEL INI SILAHKAN DIKOSONGKAN DULU
No. | Nama Anggota | Task yang dikerjakan | Tanggal Pengerjaan | Kendala yang dihadapi | Waktu Perkiraan Selesai
1 | Jennie | Membuat prototype | 3 Mei 2023 | Kesulitan mencari warna yang sesuai | 3 hari
Sprint Review |  |  | TABEL INI SILAHKAN DIKOSONGKAN DULU
Sprint 1
Completed Task | Incompleted Task | What's Next
Task 1 : Designing the prototype | Task 4 : Connecting to Database | Sprint 2 : Sprint Goal 1 As a buyer I want to…
Sprint Retrospective |  |  |  |  | TABEL INI SILAHKAN DIKOSONGKAN DULU
Sprint 1
Analysis |  | Actions
What went well? | What could be improved? | What to stop doing? | What to Keep doing? | What to Start doing?
Faster decision | Start on time | The meeting is not on time | Faster decision | Time management